§18.59	F.	Table: Time and Responsibility Schedule

| Identity |  | Abbreviations |  |
| --- | --- | --- | --- |
| Corporation |  | C |  |
| Underwriter |  | U |  |
| Letter of Credit Bank |  | B |  |
| Issuer |  | I |  |
| Bond Counsel |  | BC |  |
| Underwriter’s Counsel |  | UC |  |
| Letter of Credit Bank Counsel |  | LCC |  |
| Corporation Counsel |  | CC |  |
| Time Frame Date | Task |  | Responsibility |
| Week 1 | Adopt official intent resolution. Prepare any applications to issuer. Submit any necessary information to letter of credit bank for credit review purposes. Review corporation’s articles of incorporation, bylaws, licenses, and existing debt agreements and determine whether any issue regarding third party consents or charter documents will affect the timing of the financing. |  | C, BC, CC C, I, U C C, CC |
| Week 2 | Begin preparation of bond documents. Begin preparation of disclosure document (official statement). Analyze any liens or security interests on property to be pledged as collateral. Begin review of contracts for use or management of facilities to be financed Begin determination of use of proceeds and amount and maturity of bonds to be issued. |  | BC UC, C, CC C, CC BC, CC C, U, BC |
| Week 3 | Receive commitment from letter of credit bank. Begin preparation of letter of credit documentation. Order preliminary title report and UCC search. Begin due diligence process. |  | C, B LCC CC C, CC, UC, BC |
| Week 4 | Distribute first draft of bond documents, TEFRA hearing notice, disclosure documents, bond purchase agreement, and related underwriting documents. |  | BC, UC |
| Week 5 | Meet to negotiate draft documents and approve draft TEFRA notice. Publish TEFRA notice. Appoint trustee. |  | All hands BC C, U |
| Week 6 | Revise and recirculate bond documents and disclosure documents Distribute first draft of letter of credit documents and related security documents. Submit documents to issuer and form of approving issuer resolution. Prepare approving board resolution. |  | BC, UC LCC BC C, CC |
| Week 7 | Meet to discuss revised drafts of documents. Board meets to approve documents and financing. Complete due diligence process. Determine any necessary payoffs of prior loans secured by collateral and arrange for releases from creditors necessary for closing. |  | All hands C, CC C, CC, UC, BC C, CC |
| Week 8 | TEFRA hearing. Issuer meeting to approve bond documents. Circulate final drafts of bond and underwriting documents and revised drafts of letter of credit documents. Print and mail preliminary official statement. |  | I, BC, C I, BC, C BC, UC, LCC U |
| Week 9 | Price bonds and sign bond purchase agreement. Finalize and mail final official statement. Begin preparation of closing documents and legal opinions. |  | U, I, C U, UC BC, UC, LCC |
| Week 10 or 11 | Preclose and close bond issue. |  | All hands |